## Sheet1
PRIMARY COLUMN | START DATE | END DATE | DURATION | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH
1.0 Requirements Analysis | 2017-11-13 | 2018-01-02 | 50 days
Data Gathering | 2017-11-13 | 2017-11-20 | 7 days
Documentation Chapter 1-3 | 2017-11-20 | 2017-12-04 | 14 days
Data Gathering | 2017-12-04 | 2017-12-18 | 14 days
Finalizing Documentation Chapter 1-3 | 2017-12-18 | 2017-12-24 | 6 days
Data Gathering | 2017-12-24 | 2017-12-27 | 3days
Major Revision Documentation Chapter 1-3 | 2017-12-27 | 2018-01-02 | 6 days
2.0 Design | 2018-01-02 | 2018-01-31 | 29 days
System Design User Interface | 2018-01-02 | 2018-01-17 | 15 days
System Design Admin Interface | 2018-01-17 | 2018-01-31 | 14 days
3.0 Implementation | 2018-02-01 | 2017-02-28 | 28 days
System Functionality User Interface | 2018-02-01 | 2018-02-14 | 14 days
System Functionality Admin Interface | 2018-02-15 | 2018-02-28 | 14 days
4.0 Testing | 2018-03-01 | 2018-03-13 | 12 days
System Usability Test Scale | 2018-03-01 | 2018-03-06 | 6 days
Functional Testing | 2018-03-07 | 2018-03-13 | 6 days
5.0 Maintainance | 2018-03-14 | 2018-03-24 | 10 days
Maintainance | 2018-03-14 | 2018-03-24 | 10 days